## Project Schedule
-
-
-
|  |  | Project Schedule | [80 empty] | - | time axis 2016-09-25 to 2018-03-04
|  | # | DEPARTMENT | Bid Days | Days Scheduled | Variance | Week- 1 | Week- 2 | Week- 3 | Week- 4 | Week- 5 | Week- 6 | Week- 7 | Week- 8 | Week- 9 | Week- 10 | Week- 11 | Week- 12 | Week- 13 | Week- 14 | Week- 15 | Week- 16 | Week- 17 | Week- 18 | Week- 19 | Week- 20 | Week- 21 | Week- 22 | Week- 23 | Week- 24 | Week- 25 | Week- 26 | Week- 27 | Week- 28 | Week- 29 | Week- 30 | Week- 31 | Week- 32 | Week- 33 | Week- 34 | Week- 35 | Week- 36 | Week- 37 | Week- 38 | Week- 39 | Week- 40 | Week- 41 | Week- 42 | Week- 43 | Week- 44 | Week- 45 | Week- 46 | Week- 47 | Week- 48 | Week- 49 | Week- 50 | Week- 51 | Week- 52 | Week- 53 | Week- 54 | Week- 55 | Week- 56 | Week- 57 | Week- 58 | Week- 59 | Week- 60 | Week- 61 | Week- 62 | Week- 63 | Week- 64 | Week- 65 | Week- 66 | Week- 67 | Week- 68 | Week- 69 | Week- 70 | Week- 71 | Week- 72 | Week- 73 | Week- 74 | Week- 75 | Week- 76 |  | -
[7 empty] | 2017-01-29: Holiday |  | -
|  | PRE PRODUCTION | 0 | 0 | 0 | 0 | [77 empty] | -
|  |  | Story | 25 | 25 | 0 | [77 empty] | - | bar: 2016-09-25 to 2016-10-23
|  |  | Script | 30 | 30 | 0 | [77 empty] | - | bar: 2016-10-09 to 2016-11-13
|  |  | Concept | 60 | 60 | 0 | 2016-10-30: 2; 2016-11-06: 2; 2016-11-13: 2; 2016-11-20: 2; 2016-11-27: 2; 2016-12-04: 2 |  | -
|  |  | Story Board | 90 | 90 | 0 | 2016-11-13: 2; 2016-11-20: 2; 2016-11-27: 2; 2016-12-04: 2; 2016-12-11: 2; 2016-12-18: 2; 2016-12-25: 2; 2017-01-01: 2; 2017-01-08: 2 |  | -
|  |  | Animatic | 80 | 80 | 0 | 2016-11-27: 2; 2016-12-04: 2; 2016-12-11: 2; 2016-12-18: 2; 2016-12-25: 2; 2017-01-01: 2; 2017-01-08: 2; 2017-01-15: 2 |  | -
|  |  | Asset Designs | 90 | 90 | 0 | 2016-12-11: 2; 2016-12-18: 2; 2016-12-25: 2; 2017-01-01: 2; 2017-01-08: 2; 2017-01-15: 2; 2017-01-22: 2; 2017-02-05: 2; 2017-02-12: 2 |  | -
-
|  | CHARACTER BUILD | C Modeling | 400 | 400 | 0 | 2017-01-15: 5; 2017-01-22: 5; 2017-02-05: 5; 2017-02-12: 5; 2017-02-19: 5; 2017-02-26: 5; 2017-03-05: 5; 2017-03-12: 5; 2017-03-19: 5; 2017-03-26: 5; 2017-04-02: 5; 2017-04-09: 5; 2017-04-16: 5; 2017-04-23: 5; 2017-04-30: 5; 2017-05-07: 5 |  | -
|  |  | C Facial | 160 | 160 | 0 | 2017-02-05: 2; 2017-02-12: 2; 2017-02-19: 2; 2017-02-26: 2; 2017-03-05: 2; 2017-03-12: 2; 2017-03-19: 2; 2017-03-26: 2; 2017-04-02: 2; 2017-04-09: 2; 2017-04-16: 2; 2017-04-23: 2; 2017-04-30: 2; 2017-05-07: 2; 2017-05-14: 2; 2017-05-21: 2 |  | -
|  |  | C Surfacing | 665 | 665 | 0 | 2017-02-05: 7; 2017-02-12: 7; 2017-02-19: 7; 2017-02-26: 7; 2017-03-05: 7; 2017-03-12: 7; 2017-03-19: 7; 2017-03-26: 7; 2017-04-02: 7; 2017-04-09: 7; 2017-04-16: 7; 2017-04-23: 7; 2017-04-30: 7; 2017-05-07: 7; 2017-05-14: 7; 2017-05-21: 7; 2017-05-28: 7; 2017-06-04: 7; 2017-06-11: 7 |  | -
|  |  | C Look Development | 240 | 240 | 0 | 2017-02-05: 2; 2017-02-12: 2; 2017-02-19: 2; 2017-02-26: 2; 2017-03-05: 2; 2017-03-12: 2; 2017-03-19: 2; 2017-03-26: 2; 2017-04-02: 2; 2017-04-09: 2; 2017-04-16: 2; 2017-04-23: 2; 2017-04-30: 2; 2017-05-07: 2; 2017-05-14: 2; 2017-05-21: 2; 2017-05-28: 2; 2017-06-04: 2; 2017-06-11: 2; 2017-06-18: 2; 2017-06-25: 2; 2017-07-02: 2; 2017-07-09: 2; 2017-07-16: 2 |  | -
|  |  | C Rigging | 360 | 360 | 0 | 2017-02-05: 4; 2017-02-12: 4; 2017-02-19: 4; 2017-02-26: 4; 2017-03-05: 4; 2017-03-12: 4; 2017-03-19: 4; 2017-03-26: 4; 2017-04-02: 4; 2017-04-09: 4; 2017-04-16: 4; 2017-04-23: 4; 2017-04-30: 4; 2017-05-07: 4; 2017-05-14: 4; 2017-05-21: 4; 2017-05-28: 4; 2017-06-04: 4 |  | -
|  |  | C Hair/ Fur | 270 | 270 | 0 | 2017-02-05: 3; 2017-02-12: 3; 2017-02-19: 3; 2017-02-26: 3; 2017-03-05: 3; 2017-03-12: 3; 2017-03-19: 3; 2017-03-26: 3; 2017-04-02: 3; 2017-04-09: 3; 2017-04-16: 3; 2017-04-23: 3; 2017-04-30: 3; 2017-05-07: 3; 2017-05-14: 3; 2017-05-21: 3; 2017-05-28: 3; 2017-06-04: 3 |  | -
-
|  | SET BUILD | Modeling | 640 | 640 | 0 | 2017-01-15: 8; 2017-01-22: 8; 2017-02-05: 8; 2017-02-12: 8; 2017-02-19: 8; 2017-02-26: 8; 2017-03-05: 8; 2017-03-12: 8; 2017-03-19: 8; 2017-03-26: 8; 2017-04-02: 8; 2017-04-09: 8; 2017-04-16: 8; 2017-04-23: 8; 2017-04-30: 8; 2017-05-07: 8 |  | -
|  |  | Surfacing | 1140 | 1140 | 0 | 2017-02-05: 12; 2017-02-12: 12; 2017-02-19: 12; 2017-02-26: 12; 2017-03-05: 12; 2017-03-12: 12; 2017-03-19: 12; 2017-03-26: 12; 2017-04-02: 12; 2017-04-09: 12; 2017-04-16: 12; 2017-04-23: 12; 2017-04-30: 12; 2017-05-07: 12; 2017-05-14: 12; 2017-05-21: 12; 2017-05-28: 12; 2017-06-04: 12; 2017-06-11: 12 |  | -
|  |  | Look Development | 190 | 190 | 0 | 2017-02-05: 2; 2017-02-12: 2; 2017-02-19: 2; 2017-02-26: 2; 2017-03-05: 2; 2017-03-12: 2; 2017-03-19: 2; 2017-03-26: 2; 2017-04-02: 2; 2017-04-09: 2; 2017-04-16: 2; 2017-04-23: 2; 2017-04-30: 2; 2017-05-07: 2; 2017-05-14: 2; 2017-05-21: 2; 2017-05-28: 2; 2017-06-04: 2; 2017-06-11: 2 |  | -
|  |  | Rigging | 95 | 95 | 0 | [77 empty] | - | bar: 2017-02-05 to 2017-06-11
|  |  | Foliage | 190 | 190 | 0 | 2017-02-05: 2; 2017-02-12: 2; 2017-02-19: 2; 2017-02-26: 2; 2017-03-05: 2; 2017-03-12: 2; 2017-03-19: 2; 2017-03-26: 2; 2017-04-02: 2; 2017-04-09: 2; 2017-04-16: 2; 2017-04-23: 2; 2017-04-30: 2; 2017-05-07: 2; 2017-05-14: 2; 2017-05-21: 2; 2017-05-28: 2; 2017-06-04: 2; 2017-06-11: 2 |  | -
|  |  | Matte Painting | 195 | 195 | 0 | [77 empty] | - | bar: 2017-02-05 to 2017-10-29
-
|  | PROP BUILD | Modeling | 160 | 160 | 0 | 2017-01-15: 2; 2017-01-22: 2; 2017-02-05: 2; 2017-02-12: 2; 2017-02-19: 2; 2017-02-26: 2; 2017-03-05: 2; 2017-03-12: 2; 2017-03-19: 2; 2017-03-26: 2; 2017-04-02: 2; 2017-04-09: 2; 2017-04-16: 2; 2017-04-23: 2; 2017-04-30: 2; 2017-05-07: 2 |  | -
|  |  | Surfacing | 380 | 380 | 0 | 2017-02-05: 4; 2017-02-12: 4; 2017-02-19: 4; 2017-02-26: 4; 2017-03-05: 4; 2017-03-12: 4; 2017-03-19: 4; 2017-03-26: 4; 2017-04-02: 4; 2017-04-09: 4; 2017-04-16: 4; 2017-04-23: 4; 2017-04-30: 4; 2017-05-07: 4; 2017-05-14: 4; 2017-05-21: 4; 2017-05-28: 4; 2017-06-04: 4; 2017-06-11: 4 |  | -
|  |  | Look Development | 50 | 50 | 0 | 2017-02-05: 0.5; 2017-02-12: 0.5; 2017-02-19: 0.5; 2017-02-26: 0.5; 2017-03-05: 0.5; 2017-03-12: 0.5; 2017-03-19: 0.5; 2017-03-26: 0.5; 2017-04-02: 0.5; 2017-04-09: 0.5; 2017-04-16: 0.5; 2017-04-23: 0.5; 2017-04-30: 0.5; 2017-05-07: 0.5; 2017-05-14: 0.5; 2017-05-21: 0.5; 2017-05-28: 0.5; 2017-06-04: 0.5; 2017-06-11: 1 |  | -
|  |  | Rigging | 95 | 95 | 0 | [77 empty] | - | bar: 2017-02-05 to 2017-06-11
|  |  | Foliage | 0 | 0 | 0 | 2017-02-05: 0; 2017-02-12: 0; 2017-02-19: 0; 2017-02-26: 0; 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0; 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0; 2017-05-14: 0; 2017-05-21: 0; 2017-05-28: 0; 2017-06-04: 0; 2017-06-11: 0 |  | -
|  |  | Matte Painting | 0 | 0 | 0 | 2017-02-05: 0; 2017-02-12: 0; 2017-02-19: 0; 2017-02-26: 0; 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0; 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0; 2017-05-14: 0; 2017-05-21: 0; 2017-05-28: 0; 2017-06-04: 0; 2017-06-11: 0; 2017-06-18: 0; 2017-06-25: 0; 2017-07-02: 0; 2017-07-09: 0; 2017-07-16: 0; 2017-07-23: 0; 2017-07-30: 0; 2017-08-06: 0; 2017-08-13: 0; 2017-08-20: 0; 2017-08-27: 0; 2017-09-03: 0; 2017-09-10: 0; 2017-09-17: 0; 2017-09-24: 0; 2017-10-01: 0; 2017-10-08: 0; 2017-10-15: 0; 2017-10-22: 0; 2017-10-29: 0 |  | -
-
|  | SHOT PRODUCTION | Previz | 255 | 255 | 0 | 2016-09-25: 0; 2017-02-19: 3; 2017-02-26: 3; 2017-03-05: 3; 2017-03-12: 3; 2017-03-19: 3; 2017-03-26: 3; 2017-04-02: 3; 2017-04-09: 3; 2017-04-16: 3; 2017-04-23: 3; 2017-04-30: 3; 2017-05-07: 3; 2017-05-14: 3; 2017-05-21: 3; 2017-05-28: 3; 2017-06-04: 3; 2017-06-11: 3 |  | -
|  |  | Layout | 380 | 380 | 0 | 2016-09-25: 0; 2017-04-23: 4; 2017-04-30: 4; 2017-05-07: 4; 2017-05-14: 4; 2017-05-21: 4; 2017-05-28: 4; 2017-06-04: 4; 2017-06-11: 4; 2017-06-18: 4; 2017-06-25: 4; 2017-07-02: 4; 2017-07-09: 4; 2017-07-16: 4; 2017-07-23: 4; 2017-07-30: 4; 2017-08-06: 4; 2017-08-13: 4; 2017-08-20: 4; 2017-08-27: 4 |  | -
|  |  | Animation | 1875 | 1875 | 0 | 2016-09-25: 0; 2017-05-07: 15; 2017-05-14: 15; 2017-05-21: 15; 2017-05-28: 15; 2017-06-04: 15; 2017-06-11: 15; 2017-06-18: 15; 2017-06-25: 15; 2017-07-02: 15; 2017-07-09: 15; 2017-07-16: 15; 2017-07-23: 15; 2017-07-30: 15; 2017-08-06: 15; 2017-08-13: 15; 2017-08-20: 15; 2017-08-27: 15; 2017-09-03: 15; 2017-09-10: 15; 2017-09-17: 15; 2017-09-24: 15; 2017-10-01: 15; 2017-10-08: 15; 2017-10-15: 15; 2017-10-22: 15 |  | -
|  |  | Simulation | 500 | 500 | 0 | 2016-09-25: 0; 2017-05-21: 4; 2017-05-28: 4; 2017-06-04: 4; 2017-06-11: 4; 2017-06-18: 4; 2017-06-25: 4; 2017-07-02: 4; 2017-07-09: 4; 2017-07-16: 4; 2017-07-23: 4; 2017-07-30: 4; 2017-08-06: 4; 2017-08-13: 4; 2017-08-20: 4; 2017-08-27: 4; 2017-09-03: 4; 2017-09-10: 4; 2017-09-17: 4; 2017-09-24: 4; 2017-10-01: 4; 2017-10-08: 4; 2017-10-15: 4; 2017-10-22: 4; 2017-10-29: 4; 2017-11-05: 4 |  | -
|  |  | Effects | 1085 | 1085 | 0 | 2016-09-25: 0; 2017-05-21: 7; 2017-05-28: 7; 2017-06-04: 7; 2017-06-11: 7; 2017-06-18: 7; 2017-06-25: 7; 2017-07-02: 7; 2017-07-09: 7; 2017-07-16: 7; 2017-07-23: 7; 2017-07-30: 7; 2017-08-06: 7; 2017-08-13: 7; 2017-08-20: 7; 2017-08-27: 7; 2017-09-03: 7; 2017-09-10: 7; 2017-09-17: 7; 2017-09-24: 7; 2017-10-01: 7; 2017-10-08: 7; 2017-10-15: 7; 2017-10-22: 7; 2017-10-29: 7; 2017-11-05: 7; 2017-11-12: 7; 2017-11-19: 7; 2017-11-26: 7; 2017-12-03: 7; 2017-12-10: 7; 2017-12-17: 7 |  | -
|  |  | Lighting | 1120 | 1120 | 0 | 2016-09-25: 0; 2017-06-04: 8; 2017-06-11: 8; 2017-06-18: 8; 2017-06-25: 8; 2017-07-02: 8; 2017-07-09: 8; 2017-07-16: 8; 2017-07-23: 8; 2017-07-30: 8; 2017-08-06: 8; 2017-08-13: 8; 2017-08-20: 8; 2017-08-27: 8; 2017-09-03: 8; 2017-09-10: 8; 2017-09-17: 8; 2017-09-24: 8; 2017-10-01: 8; 2017-10-08: 8; 2017-10-15: 8; 2017-10-22: 8; 2017-10-29: 8; 2017-11-05: 8; 2017-11-12: 8; 2017-11-19: 8; 2017-11-26: 8; 2017-12-03: 8; 2017-12-10: 8 |  | -
|  |  | Compositing | 1500 | 1500 | 0 | 2016-09-25: 0; 2017-06-04: 10; 2017-06-11: 10; 2017-06-18: 10; 2017-06-25: 10; 2017-07-02: 10; 2017-07-09: 10; 2017-07-16: 10; 2017-07-23: 10; 2017-07-30: 10; 2017-08-06: 10; 2017-08-13: 10; 2017-08-20: 10; 2017-08-27: 10; 2017-09-03: 10; 2017-09-10: 10; 2017-09-17: 10; 2017-09-24: 10; 2017-10-01: 10; 2017-10-08: 10; 2017-10-15: 10; 2017-10-22: 10; 2017-10-29: 10; 2017-11-05: 10; 2017-11-12: 10; 2017-11-19: 10; 2017-11-26: 10; 2017-12-03: 10; 2017-12-10: 10; 2017-12-17: 10; 2017-12-24: 10 |  | -
|  |  | Edit | 175 | 175 | 0 | 2016-09-25: 0; 2017-05-07: 1; 2017-05-14: 1; 2017-05-21: 1; 2017-05-28: 1; 2017-06-04: 1; 2017-06-11: 1; 2017-06-18: 1; 2017-06-25: 1; 2017-07-02: 1; 2017-07-09: 1; 2017-07-16: 1; 2017-07-23: 1; 2017-07-30: 1; 2017-08-06: 1; 2017-08-13: 1; 2017-08-20: 1; 2017-08-27: 1; 2017-09-03: 1; 2017-09-10: 1; 2017-09-17: 1; 2017-09-24: 1; 2017-10-01: 1; 2017-10-08: 1; 2017-10-15: 1; 2017-10-22: 1; 2017-10-29: 1; 2017-11-05: 1; 2017-11-12: 1; 2017-11-19: 1; 2017-11-26: 1; 2017-12-03: 1; 2017-12-10: 1; 2017-12-17: 1; 2017-12-24: 1; 2017-12-31: 1 |  | -
|  |  | Total Days | 12495 | 12495 | 0 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 5 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 19 | 17 | 0 | 58.5 | 58.5 | 59.5 | 59.5 | 59.5 | 59.5 | 59.5 | 59.5 | 59.5 | 59.5 | 59.5 | 63.5 | 63.5 | 79.5 | 64.5 | 75.5 | 73.5 | 91.5 | 85 | 52 | 52 | 52 | 52 | 52 | 50 | 50 | 50 | 50 | 50 | 50 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 31 | 30 | 26 | 26 | 26 | 26 | 26 | 18 | 11 | 1 | [8 empty] | 0 |  | -
|  | Note | [81 empty] | -
|  | New departments can be added on any poin of time | [81 empty] | -
|  | Department flow is depend on company to company | [81 empty] | -
-
-
| MY SUPPORT | [82 empty] | -
-
| RENDER NODES | [82 empty] | -
|  |  | Nodes Configuration | Bit | Core | RAM( gb) | [77 empty] | -
|  |  | Render Nodes | 16 |  | 12 | 2017-05-21: 2; 2017-05-28: 2; 2017-06-04: 2; 2017-06-11: 2; 2017-06-18: 8; 2017-06-25: 8; 2017-07-02: 8; 2017-07-09: 8; 2017-07-16: 8; 2017-07-23: 8; 2017-07-30: 20; 2017-08-06: 20; 2017-08-13: 20; 2017-08-20: 20; 2017-08-27: 20; 2017-09-03: 20; 2017-09-10: 20; 2017-09-17: 20; 2017-09-24: 20; 2017-10-01: 20; 2017-10-08: 20; 2017-10-15: 30; 2017-10-22: 30; 2017-10-29: 30; 2017-11-05: 30; 2017-11-12: 30; 2017-11-19: 30; 2017-11-26: 30; 2017-12-03: 30; 2017-12-10: 30; 2017-12-17: 30; 2017-12-24: 30 |  | -
|  |  | Render Nodes | 32 |  | 24 | 2017-05-21: 2; 2017-05-28: 2; 2017-06-04: 2; 2017-06-11: 2; 2017-06-18: 8; 2017-06-25: 8; 2017-07-02: 8; 2017-07-09: 8; 2017-07-16: 8; 2017-07-23: 8; 2017-07-30: 20; 2017-08-06: 20; 2017-08-13: 20; 2017-08-20: 20; 2017-08-27: 20; 2017-09-03: 20; 2017-09-10: 20; 2017-09-17: 20; 2017-09-24: 20; 2017-10-01: 20; 2017-10-08: 20; 2017-10-15: 30; 2017-10-22: 30; 2017-10-29: 30; 2017-11-05: 30; 2017-11-12: 30; 2017-11-19: 30; 2017-11-26: 30; 2017-12-03: 30; 2017-12-10: 30; 2017-12-17: 30; 2017-12-24: 30 |  | -
|  |  | Render Nodes | 64 |  | 48 | 2017-05-21: 2; 2017-05-28: 2; 2017-06-04: 2; 2017-06-11: 2; 2017-06-18: 8; 2017-06-25: 8; 2017-07-02: 8; 2017-07-09: 8; 2017-07-16: 8; 2017-07-23: 8; 2017-07-30: 20; 2017-08-06: 20; 2017-08-13: 20; 2017-08-20: 20; 2017-08-27: 20; 2017-09-03: 20; 2017-09-10: 20; 2017-09-17: 20; 2017-09-24: 20; 2017-10-01: 20; 2017-10-08: 20; 2017-10-15: 30; 2017-10-22: 30; 2017-10-29: 30; 2017-11-05: 30; 2017-11-12: 30; 2017-11-19: 30; 2017-11-26: 30; 2017-12-03: 30; 2017-12-10: 30; 2017-12-17: 30; 2017-12-24: 30 |  | -
|  |  | Render Nodes | 64 |  | 96 | 2017-05-21: 4; 2017-05-28: 4; 2017-06-04: 4; 2017-06-11: 4; 2017-06-18: 16; 2017-06-25: 16; 2017-07-02: 16; 2017-07-09: 16; 2017-07-16: 16; 2017-07-23: 16; 2017-07-30: 40; 2017-08-06: 40; 2017-08-13: 40; 2017-08-20: 40; 2017-08-27: 40; 2017-09-03: 40; 2017-09-10: 40; 2017-09-17: 40; 2017-09-24: 40; 2017-10-01: 40; 2017-10-08: 40; 2017-10-15: 60; 2017-10-22: 60; 2017-10-29: 60; 2017-11-05: 60; 2017-11-12: 60; 2017-11-19: 60; 2017-11-26: 60; 2017-12-03: 60; 2017-12-10: 60; 2017-12-17: 60; 2017-12-24: 60 |  | -
|  |  | Render Nodes | 64 |  | 192 | 2017-05-21: 4; 2017-05-28: 4; 2017-06-04: 4; 2017-06-11: 4; 2017-06-18: 16; 2017-06-25: 16; 2017-07-02: 16; 2017-07-09: 16; 2017-07-16: 16; 2017-07-23: 16; 2017-07-30: 40; 2017-08-06: 40; 2017-08-13: 40; 2017-08-20: 40; 2017-08-27: 40; 2017-09-03: 40; 2017-09-10: 40; 2017-09-17: 40; 2017-09-24: 40; 2017-10-01: 40; 2017-10-08: 40; 2017-10-15: 60; 2017-10-22: 60; 2017-10-29: 60; 2017-11-05: 60; 2017-11-12: 60; 2017-11-19: 60; 2017-11-26: 60; 2017-12-03: 60; 2017-12-10: 60; 2017-12-17: 60; 2017-12-24: 60 |  | -
|  |  | Render Nodes | 64 |  | 384 | 2017-05-21: 4; 2017-05-28: 4; 2017-06-04: 4; 2017-06-11: 4; 2017-06-18: 16; 2017-06-25: 16; 2017-07-02: 16; 2017-07-09: 16; 2017-07-16: 16; 2017-07-23: 16; 2017-07-30: 40; 2017-08-06: 40; 2017-08-13: 40; 2017-08-20: 40; 2017-08-27: 40; 2017-09-03: 40; 2017-09-10: 40; 2017-09-17: 40; 2017-09-24: 40; 2017-10-01: 40; 2017-10-08: 40; 2017-10-15: 60; 2017-10-22: 60; 2017-10-29: 60; 2017-11-05: 60; 2017-11-12: 60; 2017-11-19: 60; 2017-11-26: 60; 2017-12-03: 60; 2017-12-10: 60; 2017-12-17: 60; 2017-12-24: 60 |  | -
|  |  | Render Nodes | 128 |  | 384 | 2017-05-21: 2; 2017-05-28: 2; 2017-06-04: 2; 2017-06-11: 2; 2017-06-18: 8; 2017-06-25: 8; 2017-07-02: 8; 2017-07-09: 8; 2017-07-16: 8; 2017-07-23: 8; 2017-07-30: 20; 2017-08-06: 20; 2017-08-13: 20; 2017-08-20: 20; 2017-08-27: 20; 2017-09-03: 20; 2017-09-10: 20; 2017-09-17: 20; 2017-09-24: 20; 2017-10-01: 20; 2017-10-08: 20; 2017-10-15: 30; 2017-10-22: 30; 2017-10-29: 30; 2017-11-05: 30; 2017-11-12: 30; 2017-11-19: 30; 2017-11-26: 30; 2017-12-03: 30; 2017-12-10: 30; 2017-12-17: 30; 2017-12-24: 30 |  | -
|  |  | Total Nodes | 432 | 0 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 80 | 80 | 80 | 80 | 80 | 80 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| STORAGE SIZE |  |  |  |  | Size(tb) | [77 empty] | -
|  |  | Storage (TB) |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 20 | 25 | 25 | 25 | 25 | 25 | 50 | 50 | 50 | 50 | 75 | 75 | 75 | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 |  | -
-
-
| PROJECT MANAGEMENT TEAM | [82 empty] | -
|  |  | Producer | 325 |  | 12 | [77 empty] | - | bar: 2016-09-25 to 2018-03-04
|  |  | Production Manager | 325 |  | 24 | [77 empty] | - | bar: 2016-09-25 to 2018-03-04
|  |  | Sequence Producer | 150 |  | 48 | [77 empty] | - | bar: 2016-09-25 to 2018-03-04
|  |  | Asset Build Manager | 185 |  | 96 | [77 empty] | - | bar: 2016-09-25 to 2018-03-04
|  |  | Project Co-ordinator | 325 |  | 192 | [77 empty] | - | bar: 2016-09-25 to 2018-03-04
|  |  | Previz+ Layout Department Head | 35 |  | 384 | 2017-02-19: 0.25; 2017-02-26: 0.25; 2017-03-05: 0.25; 2017-03-12: 0.25; 2017-03-19: 0.25; 2017-03-26: 0.25; 2017-04-02: 0.25; 2017-04-09: 0.25; 2017-04-16: 0.25; 2017-04-23: 0.25; 2017-04-30: 0.25; 2017-05-07: 0.25; 2017-05-14: 0.25; 2017-05-21: 0.25; 2017-05-28: 0.25; 2017-06-04: 0.25; 2017-06-11: 0.25; 2017-06-18: 0.25; 2017-06-25: 0.25; 2017-07-02: 0.25; 2017-07-09: 0.25; 2017-07-16: 0.25; 2017-07-23: 0.25; 2017-07-30: 0.25; 2017-08-06: 0.25; 2017-08-13: 0.25; 2017-08-20: 0.25; 2017-08-27: 0.25 |  | -
|  |  | Animation Department Head | 62.5 |  |  | 2017-05-07: 0.5; 2017-05-14: 0.5; 2017-05-21: 0.5; 2017-05-28: 0.5; 2017-06-04: 0.5; 2017-06-11: 0.5; 2017-06-18: 0.5; 2017-06-25: 0.5; 2017-07-02: 0.5; 2017-07-09: 0.5; 2017-07-16: 0.5; 2017-07-23: 0.5; 2017-07-30: 0.5; 2017-08-06: 0.5; 2017-08-13: 0.5; 2017-08-20: 0.5; 2017-08-27: 0.5; 2017-09-03: 0.5; 2017-09-10: 0.5; 2017-09-17: 0.5; 2017-09-24: 0.5; 2017-10-01: 0.5; 2017-10-08: 0.5; 2017-10-15: 0.5; 2017-10-22: 0.5 |  | -
|  |  | Total Days | 1407.5 | 0 | 756 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.75 | 4.75 | 4.75 | 4.75 | 5.75 | 5.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| MIS TEAM | [82 empty] | -
|  |  | MIS Manager | 81.25 |  | 12 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [11 empty] | -
|  |  | MIS Executive-1 | 162.5 |  | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [11 empty] | -
|  |  | MIS Executive-2 | 220 |  | 48 | [77 empty] | - | bar: 2016-09-25 to 2018-03-04
|  |  | Total Days | 463.75 | 0 | 84 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0.75 | 0.75 | 0.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| TECHNOLOGY TEAM | [82 empty] | -
|  |  | Tech Manager | 81.25 |  | 12 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [11 empty] | -
|  |  | Developer- 1 | 162.5 |  | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [11 empty] | -
|  |  | Developer- 2 | 85 |  | 24 | 2016-09-25: 0.5; 2016-10-02: 0.5; 2016-10-09: 0.5; 2016-10-16: 0.5; 2016-10-23: 0.5; 2016-10-30: 0.5; 2016-11-06: 0.5; 2016-11-13: 0.5; 2016-11-20: 0.5; 2016-11-27: 0.5; 2016-12-04: 0.5; 2016-12-11: 0.5; 2016-12-18: 0.5; 2016-12-25: 0.5; 2017-01-01: 0.5; 2017-01-08: 0.5; 2017-01-15: 0.5; 2017-01-22: 0.5; 2017-02-05: 0.5; 2017-02-12: 0.5; 2017-02-19: 0.5; 2017-02-26: 0.5; 2017-03-05: 0.5; 2017-03-12: 0.5; 2017-03-19: 0.5; 2017-03-26: 0.5; 2017-04-02: 0.5; 2017-04-09: 0.5; 2017-04-16: 0.5; 2017-04-23: 0.5; 2017-04-30: 0.5; 2017-05-07: 0.5; 2017-05-14: 0.5; 2017-05-21: 0.5 |  | -
|  |  | Developer- 3 | 107.5 |  | 24 | 2016-09-25: 0.5; 2016-10-02: 0.5; 2016-10-09: 0.5; 2016-10-16: 0.5; 2016-10-23: 0.5; 2016-10-30: 0.5; 2016-11-06: 0.5; 2016-11-13: 0.5; 2016-11-20: 0.5; 2016-11-27: 0.5; 2016-12-04: 0.5; 2016-12-11: 0.5; 2016-12-18: 0.5; 2016-12-25: 0.5; 2017-01-01: 0.5; 2017-01-08: 0.5; 2017-01-15: 0.5; 2017-01-22: 0.5; 2017-02-05: 0.5; 2017-02-12: 0.5; 2017-02-19: 0.5; 2017-02-26: 0.5; 2017-03-05: 0.5; 2017-03-12: 0.5; 2017-03-19: 0.5; 2017-03-26: 0.5; 2017-04-02: 0.5; 2017-04-09: 0.5; 2017-04-16: 0.5; 2017-04-23: 0.5; 2017-04-30: 0.5; 2017-05-07: 0.5; 2017-05-14: 0.5; 2017-05-21: 0.5; 2017-05-28: 0.5; 2017-06-04: 0.5; 2017-06-11: 0.5; 2017-06-18: 0.5; 2017-06-25: 0.5; 2017-07-02: 0.5; 2017-07-09: 0.5; 2017-07-16: 0.5; 2017-07-23: 0.5 |  | -
|  |  | Developer- 4 | 130 |  | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [24 empty] | -
|  |  | Developer- 5 | 155 |  | 48 | [77 empty] | - | bar: 2016-09-25 to 2018-03-04
|  |  | Total Days | 721.25 | 0 | 156 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 0 | 2.25 | 2.25 | 2.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| RENDER TEAM | [82 empty] | -
|  |  | Render Manager | 19 |  | 12 | 2017-04-02: 0.1; 2017-04-09: 0.1; 2017-04-16: 0.1; 2017-04-23: 0.1; 2017-04-30: 0.1; 2017-05-07: 0.1; 2017-05-14: 0.1; 2017-05-21: 0.1; 2017-05-28: 0.1; 2017-06-04: 0.1; 2017-06-11: 0.1; 2017-06-18: 0.1; 2017-06-25: 0.1; 2017-07-02: 0.1; 2017-07-09: 0.1; 2017-07-16: 0.1; 2017-07-23: 0.1; 2017-07-30: 0.1; 2017-08-06: 0.1; 2017-08-13: 0.1; 2017-08-20: 0.1; 2017-08-27: 0.1; 2017-09-03: 0.1; 2017-09-10: 0.1; 2017-09-17: 0.1; 2017-09-24: 0.1; 2017-10-01: 0.1; 2017-10-08: 0.1; 2017-10-15: 0.1; 2017-10-22: 0.1; 2017-10-29: 0.1; 2017-11-05: 0.1; 2017-11-12: 0.1; 2017-11-19: 0.1; 2017-11-26: 0.1; 2017-12-03: 0.1; 2017-12-10: 0.1; 2017-12-17: 0.1 |  | -
|  |  | Other Executive-1 | 47.5 |  | 24 | 2017-04-02: 0.25; 2017-04-09: 0.25; 2017-04-16: 0.25; 2017-04-23: 0.25; 2017-04-30: 0.25; 2017-05-07: 0.25; 2017-05-14: 0.25; 2017-05-21: 0.25; 2017-05-28: 0.25; 2017-06-04: 0.25; 2017-06-11: 0.25; 2017-06-18: 0.25; 2017-06-25: 0.25; 2017-07-02: 0.25; 2017-07-09: 0.25; 2017-07-16: 0.25; 2017-07-23: 0.25; 2017-07-30: 0.25; 2017-08-06: 0.25; 2017-08-13: 0.25; 2017-08-20: 0.25; 2017-08-27: 0.25; 2017-09-03: 0.25; 2017-09-10: 0.25; 2017-09-17: 0.25; 2017-09-24: 0.25; 2017-10-01: 0.25; 2017-10-08: 0.25; 2017-10-15: 0.25; 2017-10-22: 0.25; 2017-10-29: 0.25; 2017-11-05: 0.25; 2017-11-12: 0.25; 2017-11-19: 0.25; 2017-11-26: 0.25; 2017-12-03: 0.25; 2017-12-10: 0.25; 2017-12-17: 0.25 |  | -
|  |  | Other Executive-2 | 31 |  | 24 | 2017-05-21: 0.2; 2017-05-28: 0.2; 2017-06-04: 0.2; 2017-06-11: 0.2; 2017-06-18: 0.2; 2017-06-25: 0.2; 2017-07-02: 0.2; 2017-07-09: 0.2; 2017-07-16: 0.2; 2017-07-23: 0.2; 2017-07-30: 0.2; 2017-08-06: 0.2; 2017-08-13: 0.2; 2017-08-20: 0.2; 2017-08-27: 0.2; 2017-09-03: 0.2; 2017-09-10: 0.2; 2017-09-17: 0.2; 2017-09-24: 0.2; 2017-10-01: 0.2; 2017-10-08: 0.2; 2017-10-15: 0.2; 2017-10-22: 0.2; 2017-10-29: 0.2; 2017-11-05: 0.2; 2017-11-12: 0.2; 2017-11-19: 0.2; 2017-11-26: 0.2; 2017-12-03: 0.2; 2017-12-10: 0.2; 2017-12-17: 0.2 |  | -
|  |  | Other Executive-3 | 31 |  | 24 | 2017-05-21: 0.2; 2017-05-28: 0.2; 2017-06-04: 0.2; 2017-06-11: 0.2; 2017-06-18: 0.2; 2017-06-25: 0.2; 2017-07-02: 0.2; 2017-07-09: 0.2; 2017-07-16: 0.2; 2017-07-23: 0.2; 2017-07-30: 0.2; 2017-08-06: 0.2; 2017-08-13: 0.2; 2017-08-20: 0.2; 2017-08-27: 0.2; 2017-09-03: 0.2; 2017-09-10: 0.2; 2017-09-17: 0.2; 2017-09-24: 0.2; 2017-10-01: 0.2; 2017-10-08: 0.2; 2017-10-15: 0.2; 2017-10-22: 0.2; 2017-10-29: 0.2; 2017-11-05: 0.2; 2017-11-12: 0.2; 2017-11-19: 0.2; 2017-11-26: 0.2; 2017-12-03: 0.2; 2017-12-10: 0.2; 2017-12-17: 0.2 |  | -
|  |  | Total Days | 128.5 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| STAFFING TEAM | [82 empty] | -
|  |  | Employee -1 | 30.5 |  | 12 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [12 empty] | -
|  |  | Employee -2 | 30.5 |  | 24 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [12 empty] | -
|  |  | Total Days | 61 | 0 | 36 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| OTHERS TEAMS | [82 empty] | -
|  |  | Employee -1 | 30.5 |  | 12 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [12 empty] | -
|  |  | Employee -2 | 30.5 |  | 24 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [12 empty] | -
|  |  | Employee -3 | 30.5 |  | 24 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [12 empty] | -
|  |  | Employee -4 | 30.5 |  | 24 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [12 empty] | -
|  |  | Employee -5 | 61 |  | 24 |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [12 empty] | -
|  |  | Management | 61 |  | 24 |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [12 empty] | -
|  |  | Total Days | 244 | 0 | 132 | 0 | 0 | 0 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
-
- | - | - | - | - | - | - | [76 empty] | - | - | bar: 2016-09-25 to 2018-03-04

## Project Budget
-
-
-
|  |  | Project Budget | [79 empty] | - | time axis 2016-09-25 to 2018-03-04
|  | # | DEPARTMENT | Cost/ Week | Cost | Week- 1 | Week- 2 | Week- 3 | Week- 4 | Week- 5 | Week- 6 | Week- 7 | Week- 8 | Week- 9 | Week- 10 | Week- 11 | Week- 12 | Week- 13 | Week- 14 | Week- 15 | Week- 16 | Week- 17 | Week- 18 | Week- 19 | Week- 20 | Week- 21 | Week- 22 | Week- 23 | Week- 24 | Week- 25 | Week- 26 | Week- 27 | Week- 28 | Week- 29 | Week- 30 | Week- 31 | Week- 32 | Week- 33 | Week- 34 | Week- 35 | Week- 36 | Week- 37 | Week- 38 | Week- 39 | Week- 40 | Week- 41 | Week- 42 | Week- 43 | Week- 44 | Week- 45 | Week- 46 | Week- 47 | Week- 48 | Week- 49 | Week- 50 | Week- 51 | Week- 52 | Week- 53 | Week- 54 | Week- 55 | Week- 56 | Week- 57 | Week- 58 | Week- 59 | Week- 60 | Week- 61 | Week- 62 | Week- 63 | Week- 64 | Week- 65 | Week- 66 | Week- 67 | Week- 68 | Week- 69 | Week- 70 | Week- 71 | Week- 72 | Week- 73 | Week- 74 | Week- 75 | Week- 76 |  | -
[6 empty] | 2017-01-29: Holiday |  | -
|  | PRE PRODUCTION | 0 | 0 | 0 | [77 empty] | -
|  |  | Story | 1500 | 37500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Script | 2000 | 60000 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Concept | 1500 | 90000 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Story Board | 2000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Animatic | 1000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Asset Designs | 750 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  | CHARACTER BUILD | C Modeling | 750 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 0 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | C Facial | 750 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | C Surfacing | 1000 | 665000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | C Look Development | 750 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | C Rigging | 750 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | C Hair/ Fur | 750 | 202500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  | SET BUILD | Modeling | 750 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Surfacing | 1000 | 1140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Look Development | 750 | 142500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Rigging | 800 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Foliage | 750 | 142500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Matte Painting | 750 | 146250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  | PROP BUILD | Modeling | 750 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Surfacing | 1000 | 380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Look Development | 750 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Rigging | 800 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Foliage | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Matte Painting | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  | SHOT PRODUCTION | Previz | 1200 | 306000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Layout | 800 | 304000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Animation | 1500 | 2812500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Simulation | 750 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Effects | 1200 | 1302000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Lighting | 1700 | 1904000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Compositing | 1750 | 2625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Edit | 600 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost |  | 14726750 | 1500 | 1500 | 3500 | 3500 | 3500 | 5000 | 5000 | 9000 | 7000 | 9000 | 9000 | 7500 | 7500 | 7500 | 7500 | 7500 | 14750 | 12750 | 0 | 49725 | 49725 | 51825 | 51825 | 51825 | 51825 | 51825 | 51825 | 51825 | 51825 | 51825 | 55025 | 55025 | 78125 | 66875 | 78275 | 76775 | 107875 | 103000 | 71050 | 71050 | 71050 | 71050 | 71050 | 69550 | 69550 | 69550 | 69550 | 69550 | 69550 | 66350 | 66350 | 66350 | 66350 | 66350 | 66350 | 66350 | 66350 | 43850 | 43100 | 40100 | 40100 | 40100 | 40100 | 40100 | 26500 | 18100 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  | Note | [80 empty] | -
|  | New departments can be added on any poin of time | [80 empty] | -
|  | Department flow is depend on company to company | [80 empty] | -
-
-
| MY SUPPORT | [81 empty] | -
-
| RENDER NODES | [81 empty] | -
|  |  | Nodes Configuration | Cost/ Week | CONFIGURATION | [77 empty] | -
|  |  | Render Nodes | 25.2 | 16Bit, Core, RAM( gb)12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.4 | 50.4 | 50.4 | 50.4 | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Render Nodes | 25.2 | 32Bit, Core, RAM( gb)24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.4 | 50.4 | 50.4 | 50.4 | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Render Nodes | 33.6 | 64Bit, Core, RAM( gb)48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.2 | 67.2 | 67.2 | 67.2 | 268.8 | 268.8 | 268.8 | 268.8 | 268.8 | 268.8 | 672 | 672 | 672 | 672 | 672 | 672 | 672 | 672 | 672 | 672 | 672 | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Render Nodes | 42 | 64Bit, Core, RAM( gb)96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 168 | 168 | 168 | 672 | 672 | 672 | 672 | 672 | 672 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Render Nodes | 50.4 | 64Bit, Core, RAM( gb)192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201.6 | 201.6 | 201.6 | 201.6 | 806.4 | 806.4 | 806.4 | 806.4 | 806.4 | 806.4 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Render Nodes | 50.4 | 64Bit, Core, RAM( gb)384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201.6 | 201.6 | 201.6 | 201.6 | 806.4 | 806.4 | 806.4 | 806.4 | 806.4 | 806.4 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Render Nodes | 58.8 | 128Bit, Core, RAM( gb)384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.6 | 117.6 | 117.6 | 117.6 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 470.4 | 1176 | 1176 | 1176 | 1176 | 1176 | 1176 | 1176 | 1176 | 1176 | 1176 | 1176 | 1764 | 1764 | 1764 | 1764 | 1764 | 1764 | 1764 | 1764 | 1764 | 1764 | 1764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost |  | 259610.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856.8 | 856.8 | 856.8 | 856.8 | 3427.2 | 3427.2 | 3427.2 | 3427.2 | 3427.2 | 3427.2 | 8568 | 8568 | 8568 | 8568 | 8568 | 8568 | 8568 | 8568 | 8568 | 8568 | 8568 | 12852 | 12852 | 12852 | 12852 | 12852 | 12852 | 12852 | 12852 | 12852 | 12852 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| STORAGE SIZE |  |  | Cost/ Week | Cost | [77 empty] | -
|  |  | Total Cost | 20 | 183840 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 400 | 500 | 500 | 500 | 500 | 500 | 1000 | 1000 | 1000 | 1000 | 1500 | 1500 | 1500 | 1500 | 1500 | 2000 | 2000 | 2000 | 2000 | 2000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 |  | -
-
-
| PROJECT MANAGEMENT TEAM |  |  | Cost/ Week | Cost | [77 empty] | -
|  |  | Producer | 2000 | 130000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Production Manager | 1750 | 113750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 0 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Sequence Producer | 1000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Asset Build Manager | 1000 | 37000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Project Co-ordinator | 500 | 32500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Previz+ Layout Department Head | 500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Animation Department Head | 1250 | 15625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost | 8000 | 362375 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 0 | 5250 | 5250 | 5375 | 5375 | 5375 | 5375 | 5375 | 5375 | 5375 | 5375 | 5375 | 5375 | 5375 | 6000 | 6000 | 6000 | 6000 | 7000 | 7000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 5875 | 5875 | 5875 | 5875 | 5875 | 5875 | 5875 | 5875 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| MIS TEAM |  |  | Cost/ Week | Cost | [77 empty] | -
|  |  | MIS Manager | 750 | 12187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 0 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | MIS Executive-1 | 300 | 9750 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 0 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | MIS Executive-2 | 300 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost | 1350 | 35137.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 0 | 337.5 | 337.5 | 337.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| TECHNOLOGY TEAM |  |  | Cost/ Week | Cost | [77 empty] | -
|  |  | Tech Manager | 1000 | 16250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Developer- 1 | 500 | 16250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Developer- 2 | 500 | 8500 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Developer- 3 | 450 | 9675 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 0 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Developer- 4 | 350 | 9100 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Developer- 5 | 500 | 15500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost | 3300 | 75275 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 0 | 1150 | 1150 | 1150 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1650 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1175 | 1175 | 1175 | 1175 | 1175 | 1175 | 1175 | 1175 | 1175 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| RENDER TEAM |  |  | Cost/ Week | Cost | [77 empty] | -
|  |  | Render Manager | 1000 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Other Executive-1 | 500 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Other Executive-2 | 500 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Other Executive-3 | 450 | 2790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost | 2450 | 14440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| STAFFING TEAM |  |  | Cost/ Week | Cost | [77 empty] | -
|  |  | Employee -1 | 500 | 3050 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Employee -2 | 500 | 3050 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost | 1000 | 6100 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
-
| OTHERS TEAMS |  |  | Cost/ Week | Cost | [77 empty] | -
|  |  | Employee -1 | 350 | 2135 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Employee -2 | 400 | 2440 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Employee -3 | 600 | 3660 | 0 | 0 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Employee -4 | 500 | 3050 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Employee -5 | 500 | 6100 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Management | 2500 | 30500 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
|  |  | Total Cost | 4850 | 47885 | 0 | 0 | 0 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 0 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
-
|  |  | Total Cost |  | 15711412.9 | 8337.5 | 8337.5 | 10337.5 | 11222.5 | 11222.5 | 12722.5 | 12722.5 | 16722.5 | 14722.5 | 16722.5 | 16782.5 | 15282.5 | 15282.5 | 15282.5 | 15282.5 | 15282.5 | 22532.5 | 20532.5 | 160 | 57747.5 | 57847.5 | 60072.5 | 60872.5 | 60872.5 | 60872.5 | 61372.5 | 61372.5 | 61597.5 | 61597.5 | 62097.5 | 65297.5 | 65297.5 | 89022.5 | 77772.5 | 90719.3 | 88969.3 | 121069.3 | 116194.3 | 85814.7 | 86814.7 | 86814.7 | 86814.7 | 86814.7 | 85314.7 | 90230.5 | 90230.5 | 90230.5 | 91230.5 | 91230.5 | 87905.5 | 87905.5 | 87905.5 | 87905.5 | 87230.5 | 87230.5 | 91514.5 | 91514.5 | 68389.5 | 67639.5 | 65639.5 | 65639.5 | 65639.5 | 65639.5 | 65639.5 | 52039.5 | 42339.5 | 5600 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 |  | -
-
-
- | - | - | - | - | - | [76 empty] | - | - | bar: 2016-09-25 to 2018-03-04